## Module1
Initiative | Epic | Feature | User Story | Acceptance Criteria | Priority (MoSCoW) | Estimate | Reasoning
Enhance User Access & Security | Epic 1: User Authentication & Onboarding | Feature 1.1: Student Signup | As a student, I want to sign up with my details (name, email, enrollment ID, password) so that I can create an account and access the system. | 1. Users can create accounts with email verification. (M) 2. Duplicate details rejected with error. (M) 3. Signup completed within 2 minutes. (S) | M | 2 | Needs form, DB integration, email verification.
|  | Feature 1.2: Faculty Registration | As a faculty member, I want to register with my professional details, so that I can request access to the system pending admin approval. | 1. Faculty registration requires admin approval. (M) 2. Errors shown for invalid/duplicate entries. (M) 3. Request processed within 24 hours. (S) | M | 2 | Separate workflow + DB flag + admin dependency.
|  | Feature 1.3: Faculty Approval Workflow | As an admin, I want to review and approve or reject faculty registration requests, so that only verified faculty can access the system. | 1. Admin dashboard shows pending requests. (M) 2. Approval/rejection recorded. (M) 3. Notification sent to faculty. (S) | M | 2 | Admin dashboard + DB updates.
|  | Feature 1.4: Secure Login | As a user, I want to log in securely using my registered credentials, so that I can access my personalized dashboard. | 1. Passwords stored in encrypted form. (M) 2. Successful login redirects to correct dashboard. (M) 3. Invalid credentials trigger error message. (M) | M | 3 | Core authentication + encryption.
|  | Feature 1.5: Password Security | As a user, I want to create strong passwords, so that my account remains secure and cannot be easily hacked. | 1. Passwords never stored in plain text. (M) 2. Strong password policy enforced. (S) 3. Encryption verified during audits. (C) | M | 1 | Part of encryption setup, simple enforcement.
|  | Feature 1.6: Email Verification | As a new user, I want to verify my email address, so that my account can be activated securely. | 1. Verification link sent instantly. (M) 2. Links expire within 30 minutes. (S) 3. 90% of verifications completed in 30 seconds. (C) | S | 1 | Basic email trigger with token.
|  | Feature 1.7: Password Reset | As a user, I want to reset my password securely when I forget it, so that I can regain access to my account. | 1. Reset links sent within 1 minute. (M) 2. Links expire after 30 minutes. (S) 3. New password validated against strong policy. (M) | S | 2 | Token + email + validation workflow.
|  | Feature 1.8: Role-Based Authentication | As a user, I want to access features according to my role (student, faculty, or admin) so that unauthorized features remain inaccessible. | 1. Students, faculty, and admins land on role-specific dashboards. (M) 2. Unauthorized access blocked. (M) | M | 3 | Middleware + access control setup.
|  | Feature 1.9: Account Lock | As a user, I want my account to lock automatically after multiple failed login attempts, so that my account stays protected from brute-force attacks. | 1. Account locks after 5 failed attempts. (S) 2. Unlock requires admin approval or secure reset. (C) 3. Alerts sent for suspicious activity. (C) | C | – | Security enhancement + alert handling.
|  | Feature 1.10: Session Management | As a user, I want my sessions to expire securely and allow “stay logged in” on trusted devices, so that I can maintain convenience without compromising security. | 1. Stay-logged-in works on trusted devices. (C) 2. Secure logout ends all sessions. (S) 3. Session timeout implemented for inactivity. (S) | C | – | Session handling, token expiry setup.

## Module2
Initiative | Epic | Feature | User Story | Acceptance Criteria | Priority Using MoSCoW | Estimate | Reasoning
Enhance Student Academic Engagement & Productivity | Epic 1: Student Dashboard Module | Feature 1.1: Upcoming Deadlines | As a student, I want to view upcoming project deadlines so that I can prioritize my work. | 1. Deadlines are displayed clearly on the dashboard.(M) 2. Notifications are triggered at least 24 hours before due dates.(S) 3. Students confirm deadlines are accurate during testing.(M) | M | 2 | Requires DB fetch of deadlines + UI rendering + notifications.
|  | Feature 1.2: Project Progress Tracking | As a student, I want to see a progress bar of completed vs. pending milestones so that I can track my progress visually. | 1. Progress bars dynamically update as milestones are completed. (M) 2. Students can distinguish between completed and pending milestones.(M) 3. Data is refreshed in real-time.(S) | M | 3 | Dynamic progress bar + milestone tracking logic + refresh handling.
|  | Feature 1.3: Recent Activities | As a student, I want to view my recent submissions, updates, and feedback so that I stay updated on my activities. | 1. Dashboard shows recent submissions and updates instantly. (S) 2. Feedback appears within one day of being shared by faculty. (S) 3. Activities are listed in chronological order.(M) | S | 2 | Pulls data from submissions/feedback tables + UI feed component.
|  | Feature 1.4: To-Do List | As a student, I want to create and manage a personal to-do list so that I can plan my tasks effectively. | 1. Students can create, edit, and delete tasks. (C) 2. To-do items can be marked as complete. (C) 3. Tasks persist across sessions and devices.(S) | C | 1 | Simple CRUD operations + persistence. Standalone, low effort.
|  | Feature 1.5: Faculty Feedback Preview | As a student, I want to see recent faculty feedback on my dashboard so that I can act on guidance immediately. | 1. Feedback appears in the dashboard within one day of being submitted. (S) 2. Feedback is linked to related submissions or milestones. (M) 3. Students can acknowledge or mark feedback as read.(C) | S | 2 | Dependent on submissions; needs linking + dashboard integration.
|  | Feature 1.6: Notifications Summary | As a student, I want to view reminders and alerts on my dashboard so that I don’t miss important updates. | 1. Notifications appear for deadlines, feedback, and activities.(M) 2. Students can mark notifications as read.(S) 3. Notifications persist until addressed by the student.(M) | M | 3 | Aggregates deadlines + feedback + activities into one component.
|  | Feature 1.7: Submission Status | As a student, I want to check the status of my submissions (pending, reviewed, accepted, rejected) so that I know my current standing. | 1. Submission status updates in real-time. (S) 2. Each status (pending, reviewed, accepted, rejected) is clearly visible.(M) 3. Students confirm statuses match actual faculty actions.(M) | M | 3 | Requires status mapping + DB integration + real-time refresh.
|  | Feature 1.8: Milestone Completion Chart | As a student, I want a chart (pie or bar) of completed vs. pending milestones so that I can manage my progress clearly. | 1. Pie or bar chart is displayed on the dashboard. (M) 2. Chart updates dynamically as milestones are completed. (S) 3. Students can toggle between different chart views. (C) | S | 2 | Visualization layer on top of progress tracking.
|  | Feature 1.9: Collaboration Messages | As a student, I want a quick messages panel for communication with faculty/team so that collaboration is streamlined. | 1. Students can send and receive messages in real-time. (S) 2. Messages are accessible across web and mobile. (C) 3. Message panel is integrated directly into the dashboard. (M) | C | 5 | Real-time messaging + socket integration + dashboard UI.
|  | Feature 1.10: Dashboard Customization | As a student, I want to customize dashboard widgets (deadlines, messages, charts) so that I can personalize my experience. | 1. Students can rearrange, hide, or highlight widgets. (C) 2. Customization preferences are saved across sessions. (S) 3. Dashboard layout is responsive and works across devices. (M) | C | 3 | Requires widget system + layout persistence + responsive design.

## Module 3
Initiative | Epic | Feature | User Story | Explanation | Acceptance Criteria | Priority using MoSCoW | CURE Analysis (Cost, Utilization, Risk, Effort) | Fibonacci Estimate
Efficient User Administration & System Oversight | Epic 1: User Management Goal: Allow admins to create, update, and control user access seamlessly. | Feature 1.1: Admin Login : Only authorized admins can access the dashboard, ensuring security. | As an admin, I want to log in securely using my credentials so that I can access the admin dashboard and manage platform activities without any unauthorized access. | Essential for secure access to the system | 1. Admin must enter valid credentials (username/email + password).(M) 2. Incorrect credentials should show an error message.(M) 3. Admin should be redirected to the dashboard upon successful login.(S) | Must Have | (3, 3, 3, 2)=11 | 5
|  | Feature 1.2: Manage Users (Add, Edit, Remove, Assign Roles) : Admins can efficiently manage user accounts, ensuring proper access control. | As an admin, I want to add new users (students or faculty) manually by filling in their details so that I can create accounts for users who may not be able to sign up on their own. | Ensure proper access control and security. | 1. Admin can enter user details (name, email, role).(M) 2. The system must validate required fields before saving. (M) 3. New users should receive login credentials automatically.(S) | Should Have | (3, 3, 2, 3)=11 | 2
|  |  | As an admin, I want to view a list of all registered users, including students and faculty so that I can keep track of who is using the system and manage them when necessary. | Allows efficient management of users. | 1. User list should display name, role, and account status.(M) 2. Admin should be able to search users by name or role.(S) 3. The list should update when new users are added.(M) | Must Have | (2, 2, 2, 2)=8 | 3
|  | Feature 1.3: Approve Faculty Registrations: Only verified faculty members gain access to the platform. | As an admin, I want to review and approve or reject faculty registration requests so that only verified and authorized faculty members are allowed to access the platform. | Ensures only valid faculty members have access. | 1. Pending faculty requests should be visible to the admin.(M) 2. Admin can approve or reject with a single action. (M) 3. Faculty should be notified of approval/rejection. (S) | Must Have | (3, 2, 3, 3)=11 | 5
|  | Feature 1.4: Update User Information : Admins ensure correct and up-to-date user information. | As an admin, I want to edit or update user details such as name, email, or role so that user information stays correct and up to date in the system. | Ensures data accuracy and prevents errors. | 1. Admin should be able to modify existing user details. (M) 2. System should validate input before saving updates. (M) 3. Updated information should be reflected immediately in the user list. (S) | Should Have | (3, 2, 3, 3)=11 | 3
|  | Feature 1.5: Deactivate or Remove Users : Admins prevent unauthorized access by deactivating or removing inactive users. | As an admin, I want to temporarily deactivate or permanently remove user accounts so that inactive or unauthorized users cannot misuse the system. | Prevents unauthorized access. | 1. Admin can select whether to deactivate or delete a user. (M) 2. Deactivated users cannot log in but their data remains in the system. (S) 3. Deleted users are removed permanently after confirmation. (M) | Should Have | (3, 3, 3, 2)=11 | 5
| Epic 2: Activity Monitoring Goal: Track user and system activity to improve accountability and detect unusual behavior. | Feature 2.1: Monitor General Activities : Helps admins monitor user behavior to detect issues or irregularities. | As an admin, I want to see a simple record of important actions, such as new registrations, project submissions, or evaluations so that I can stay informed about how the platform is being used. | Improves monitoring and accountability. | 1. Activity log should display key actions with timestamp and username. (M) 2. Admin can filter logs by activity type (e.g., registration, submission). (S) 3. Logs should update automatically when new activities occur. (C) | Could Have | (2, 2, 2, 2)=8 | 3
|  | Feature 2.2: Basic Reports : Admins gain insights into platform usage through system-generated reports. | As an admin, I want to generate simple reports that show the total number of students, faculty, and submissions so that I can get an overall summary of system usage when needed. | Provides quick insights for decision-making. | 1. Reports must show counts of students, faculty, and submissions. (M) 2. Reports should be downloadable in PDF or Excel format. (S) 3. Report generation should complete within a few seconds. (C) | Wont't Have | (2, 2, 2, 3)=9 | 2

## Module 4
Initiative | Epic | Feature | User Story | User Story | Priority Using MoSCoW | CURE Analysis | Estimate (Fibonacci) | Reasoning
Faculty Dashboard Module | Epic 1: Faculty Dashboard | Feature 1.1: View Submissions | As a faculty member, I want to view all student submissions for each milestone so that I can easily track and evaluate progress. | 1. Dashboard displays a list of all students and their submissions for all milestones. 2. Filters for milestone type (synopsis, mid-term, final). 3. Accessible in one view. | M | High | 3 | Core faculty need; requires data aggregation + filtering logic.
|  | Feature 1.2: Rubric-Based Evaluation | As a faculty member, I want to grade students based on predefined rubrics so that evaluations are consistent and fair. | 1. Faculty can select rubric templates (clarity, originality, presentation). 2. Each criterion has a score field. 3. Total score auto-calculates. | M | High | 3 | Rubric design + scoring automation needed; critical for fair assessment.
|  | Feature 1.3: Written Feedback | As a faculty member, I want to add comments and suggestions during evaluation so that students understand areas of improvement. | 1. Comment box available within evaluation page. 2. Faculty can add personalized text feedback. 3. Feedback saved and visible to student after submission. | S | Medium | 2 | Simple comment box integration + DB link; adds usability, not core blocker.
|  | Feature 1.4: Multi-Milestone Tabs | As a faculty member, I want to evaluate multiple milestones (synopsis, mid-term, final) so that the complete project lifecycle is assessed. | 1. Tabs for all milestones available in dashboard. 2. Faculty can switch between milestones easily. 3. Data loads dynamically without re-login. | M | High | 3 | Requires tabbed navigation + dynamic loading; essential for project flow.
|  | Feature 1.5: Edit/Update Evaluation | As a faculty member, I want to edit my evaluations so that I can correct errors or add details later. | 1. Faculty can edit evaluation scores and comments. 2. Version history maintained for transparency. 3. Notifications sent to student on updates. | C | Medium | 2 | Update + version history + notifications; useful but not mandatory initially.
|  | Feature 1.6: Confidential Feedback | As a faculty member, I want to keep my feedback visible only to the respective student so that privacy is maintained. | 1. Feedback visible only to assigned student. 2. No unauthorized user can access feedback. 3. System tested for role-based access control. | M | High | 3 | Role-based access control + permissions setup; security-critical feature.

## Module 5
Initiative | Epic | Feature | User Story | Acceptance Criteria | Priority Using MOSCOW | CURE Analysis | SP (Fibonacci) | Reasoning
Enhance Academic Transparency & Student Progress Tracking | Epic 1: Project Submission & Milestones | Feature 1.1: File Upload Benefit Hypothesis: Students can reliably upload project files for faculty review, reducing confusion and missed submissions. | As a student, I want to upload my project files so that the faculty can review them. | 1. Student can upload files in multiple supported formats (PDF, DOCX, ZIP, MP4, etc.) : M 2. Upload size limits and allowed formats are clearly defined. : M 3. Error message is displayed for unsupported formats or failed uploads :M 4. Upload is stored securely and accessible to faculty :M | M M M M | (3,3,3,2)=11 (3,2,2,1)= 8 (3,3,3,2)=11 (3,3,3,3)= 12 | 3 | Mirrors Epic 2’s Secure File Upload (existing validators, storage, and encryption patterns).
|  | Feature 1.2: Version Control Benefit Hypothesis: Students and faculty can track progress across multiple submissions, improving transparency and accountability | As a student, I want to submit multiple versions of my project so that progress is visible over time. | 1. Student can upload a new version while keeping old versions intact: M 2. Faculty can view all previous versions with timestamps :S 3. System highlights the latest version as the active submission: M | M S M | (3,3,3,2)= 11 (2,2,1,2)= 7 (3,3,3,1)= 10 | 3 | Reuses Epic 2’s Version Control model (version table + timestamps + latest flag).
|  | Feature 1.3: Milestone Updates Benefit Hypothesis: Students can transparently update project milestones, helping faculty track progress effectively | As a student, I want to update my milestones after completion so that my progress is transparent. | 1. Student can mark milestones as completed with date and notes: S 2. Faculty can view milestone updates in real-time: S 3. System ensures milestone history is maintained (no overwriting): M | S S M | (2,2,1,1)= 6 (2,2,2,3)= 9 (3,3,3,2)= 11 | 2 | Lightweight CRUD with audit trail; can leverage existing activity log patterns.
|  | Feature 1.4: Submission Confirmation Benefit Hypothesis: Students gain confidence that their work has been successfully submitted, reducing anxiety and errors | As a student, I want confirmation after every upload so that I know my submission is successful. | 1. Student receives real-time confirmation via in-app notification: M 2. Optional email confirmation is sent for every successful upload: C 3. Failed uploads trigger error messages with retry options : M | M C M | (3,3,3,1)= 10 (1,1,1,1)= 4 (3,3,3,2)= 11 | 2 | Small UI + hook on upload success/fail; reuse notifier + email service from platform.

## Module 6
Initiative | Epic | Feature | User Story | Acceptance Criteria | Estimate | Priority | Reasoning
Enhance Evaluation Transparency & Feedback Quality (Objective: Provide a structured, fair, and consistent evaluation process with clear feedback for students and comprehensive oversight for faculty/admins.) | Epic 1: Faculty Evaluation Tools Goal: Allow faculty to effectively assess student submissions and provide constructive feedback. | Feature 1.1: Faculty Access Submissions | As a faculty member, I want to view all student submissions for each milestone so that I can easily track and evaluate progress. | - Faculty can view submissions milestone-wise. - Files are accessible in supported formats. - Submissions are linked to student profiles. | 2 | H | Low complexity (filtering + display only).
|  | Feature 1.2: Rubric-Based Evaluation | As a faculty member, I want to grade students based on predefined rubrics so that evaluations are consistent and fair. | - Rubric criteria are defined and visible during evaluation. - Scores can be assigned per rubric item. - Final grade auto-calculated from rubric scores. | 3 | H | Medium aggregation + rubric logic adds complexity.
|  | Feature 1.3: Provide Written Feedback | As a faculty member, I want to add comments and suggestions during evaluation so that students understand areas of improvement. | - Faculty can add textual feedback with each evaluation. - Feedback saved along with rubric scores. - Students can view comments in their dashboard. | 2 | H | REST endpoints + error handling + persistence.
|  | Feature 1.4: Multi-Milestone Evaluation | As a faculty member, I want to evaluate multiple milestones (synopsis, mid-term, final) so that the complete project lifecycle is assessed. | - Milestones are categorized and listed separately. - Faculty can input grades per milestone. - System aggregates milestone evaluations. | 3 | M | Dashboard view + pagination + usability = high effort.
|  | Feature 1.5: Edit/Update Evaluation | As a faculty member, I want the ability to edit my evaluations so that I can correct errors or add details later. | - Faculty can reopen and edit evaluations before final lock. - Changes are timestamped and logged. - Updated feedback replaces old one in student view. | 2 | M | REST endpoints + error handling + persistence.
| Epic 2: Student Feedback Access Goal: Ensure students can view evaluations, track performance, and improve work based on faculty guidance. | Feature 2.1: Student Feedback View | As a student, I want to see my grades and faculty comments in my dashboard so that I can improve my work before the final evaluation. | - Student dashboard displays grades + comments. - Feedback appears milestone-wise. - Only respective student can view their feedback. | 2 | H | Feedback retrieval + minor fixes = low-medium.
|  | Feature 2.2: Evaluation History | As a student, I want to access past evaluation records so that I can compare my performance across milestones. | - System stores past evaluations in history. - Students can access previous scores anytime. - Data is displayed in chronological order. | 2 | M | Dashboard view + pagination + usability = high effort.
| Epic 3: System & Admin Evaluation Tools Goal: Automate evaluation storage and enable report generation for institutional insights. | Feature 3.1: Automated Score Storage | As a system, I want to automatically save evaluation data in the database so that no grading information is lost. | - All evaluations are auto-stored upon submission. - Database backups maintain data integrity. - Evaluation is retrievable anytime. | 2 | M | Backend query + filtering + UI list = medium effort.
|  | Feature 3.2: Confidential Feedback | As a faculty member, I want to keep my feedback visible only to the respective student so that privacy is maintained. | - Feedback visible only to evaluated student. - No other students can access peer evaluations. - Admin retains read-only access for audit purposes. | 2 | L | File preview/attachments = low-medium.
|  | Feature 3.3: Evaluation Reports | As an admin, I want to generate evaluation reports for all students so that project performance can be analyzed institution-wide. | - Admin can export evaluation reports (PDF/Excel). - Reports can be filtered by student, faculty, or milestone. - Aggregated performance analytics available. | 3 | M | Schema changes + audit trail = medium-high effort.

## Module 7
Initiative | Epic | Feature | User Story | Acceptance Criteria | Priority Using MoSCoW | Estimate | Reasoning
Improve Communication and Timeliness in Project Management | Epic 1: Automated Notifications and Reminders | Feature 1.1: Deadline Reminders | As a student, I want to receive automated reminders about upcoming project deadlines so that I can stay proactive and avoid missing important submissions. | 1. Reminders should be sent via in-app notifications and email when a deadline is approaching (e.g., 3 days, 1 day, and on the day). (M) 2. The reminder must include details like the project name, milestone, and due date. (M) 3. Students should only receive reminders for their assigned projects. (M) | M | 3 | Core automated reminder functionality requires scheduling logic (e.g., cron jobs) + basic integration with email and in-app systems + targeted DB queries - moderate complexity but essential for the reminder aspect of the optional module.
|  | Feature 1.2: Submission Notifications | As a faculty member, I want to receive notifications when a student submits a project or milestone update so that I can review and provide feedback in a timely manner. | 1. Notifications should be triggered immediately upon submission and sent via in-app and email. (M) 2. The notification must include the student's name, project details, and a link to the submission. (M) 3. Faculty should only receive notifications for students they are assigned to guide. (M) | M | 3 | Event-triggered notifications on submissions + email/in-app delivery + assignment-based filtering from DB - similar moderate effort to real-time alerts, key for faculty awareness in an optional module.
|  | Feature 1.3: Feedback Notifications | As a student, I want to receive notifications when faculty provides feedback on my submission so that I can quickly review suggestions and make necessary improvements. | 1. Notifications should be sent via in-app and email as soon as feedback is posted. (M) 2. The notification must include the project/milestone name, a summary of the feedback, and a link to view details. (M) 3. Students can mark the notification as read to clear it from their dashboard. (S) | S | 2 | Trigger on feedback events + simple delivery mechanisms + optional read status DB update - lower complexity, builds on existing flows, suitable as should-have since module is optional.
|  | Feature 1.4: Project Update Notifications | As a faculty member, I want to receive notifications for any updates or changes to project milestones by students so that I can monitor progress and offer guidance without constant manual checking. | 1. Notifications should trigger on milestone updates, including details like what was changed and by whom. (M) 2. Sent via in-app and email, with a direct link to the updated project section. (M) 3. Faculty can opt to mute notifications for specific projects if needed. (C) | S | 3 | Update detection logic + notification sending + mute option with user settings - moderate complexity from change tracking, demoted to should-have as not critical for basic optional notifications.
|  | Feature 1.5: System Event Notifications | As an admin, I want to receive notifications for key system events, such as new faculty registration requests so that I can approve or manage them promptly to maintain system security. | 1. Notifications should be sent via in-app and email for events like pending approvals or unusual activities. (M) 2. Include event details, timestamp, and a link to the admin dashboard for action. (M) 3. Admins can configure which event types trigger notifications. (S) | M | 2 | Hooks for system events + admin-targeted delivery + basic config - low to moderate effort, could-have as it extends beyond core student-faculty interactions in an optional module.
| Epic 2: Notification Management and Customization | Feature 2.1: Notification Preferences | As a user (student, faculty, or admin), I want to customize my notification preferences, such as choosing email, in-app, or push notifications so that I can receive alerts in the way that best suits my workflow. | 1. Users can access a settings page to select notification types and frequencies. (M) 2. Changes should save immediately and apply to future notifications. (M) 3. Default settings should include both in-app and email for critical alerts like deadlines. (S) | C | 3 | Settings UI for all roles + DB persistence + integration into notification logic - moderate complexity due to user-specific variations, should-have for personalization in optional module.
|  | Feature 2.2: Notification History | As a user (student, faculty, or admin), I want to view a history of past notifications in my dashboard so that I can reference previous alerts and ensure nothing was missed. | 1. Notification history should display in chronological order with read/unread status. (M) 2. Users can filter by type (e.g., reminders, submissions) or date range. (S) 3. History should archive automatically after a set period (e.g., 30 days) but remain searchable. (C) | W | 2 | Logging notifications in DB + dashboard UI with filters + auto-archive - straightforward data handling, could-have as it's a nice-to-have feature for an optional module.
|  | Feature 2.3: Manual Notifications | As a faculty member, I want to send manual notifications to assigned students, such as reminders or announcements so that I can communicate important updates outside of automated triggers. | 1. Faculty can compose and send notifications via a simple form, selecting recipients from their assigned students. (M) 2. Notifications should support text and attachments, sent via in-app and email. (S) 3. Sent notifications should log in the sender's history for reference. (S) | C | 5 | Form UI for composition + recipient selection + attachment support + logging - higher complexity from input validation and extras, could-have since manual sending is advanced for an optional module.

## Module 8
Initiative | Epic | Feature | User Story | Acceptance Criteria | priority | Estimate | Reasons
Enhance Transparency & Data-Driven Decisions | Epic 2: Reports & Analytics Module | Feature 2.1: Submission Progress Reports | 1. As a student, I want to view my project submission history so that I can track my deadlines and progress. 2. As a faculty supervisor, I want to generate progress reports for all my students so that I can monitor completion rates. 3. As a student, I want to receive alerts for missed deadlines so that I can take corrective action. | 1.Students can see a timeline of their submissions (uploaded files, deadlines, statuses).(M) 2.Faculty can view submission completion percentages per student/team.(M) 3.Reports are updated in real time after every submission.(M) 4. Users can export reports in Excel/PDF formats.(S) 5. Students receive alerts for missed or late submissions.(M) | M | 3 | Mix of medium + one high (real-time sync)
|  | Feature 2.2: Evaluation Overview | 1. As a faculty member, I want to download evaluation summaries so that I can keep grading records. 2. As an admin, I want to view department-wide evaluation statistics so that I can ensure consistency. 3. As a faculty member, I want to compare grading trends across semesters so that I can improve fairness. | 1. Faculty can filter evaluations by student, team, or category.(M) 2. Admin can generate department-level evaluation reports.(M) 3. Export to Excel/PDF is supported.(S) 4. Access is role-based (students cannot see faculty-level data).(M) 5. Grading trends comparison charts are available for faculty.(S) . | M | 3 | Medium aggregation + high security complexity
|  | Feature 2.3: Admin Performance Reports | 1. As an admin, I want to generate overall performance reports so that I can present insights in meetings. 2. As an admin, I want to track faculty grading activity so that I can ensure evaluations are completed on time. 3. As an admin, I want to identify students at risk (low progress, repeated delays) so that interventions can be planned. | 1. Admin can see submission and evaluation metrics across all departments.(M) 2. Faculty activity (number of evaluations done, pending, delays) is logged.(S) 3. Reports are accurate and comply with data security standards.(M) 4. User satisfaction with admin reporting is ≥ 4.5/5.(S) 5. Risk alerts are generated for underperforming students.(M) | M | 3 | Medium dashboards + high compliance/security
|  | Feature 2.4: Data Visualization Dashboards | 1. As a student, I want to see my progress in charts and graphs so that I can understand performance trends. 2. As a faculty member, I want a dashboard view of all my students so that I can quickly identify who is falling behind. 3. As an admin, I want department-wide dashboards so that I can visualize performance across multiple dimensions. | 1.Students can see charts showing their progress over time.(M) 2. Faculty dashboard shows heatmaps or color codes for student performance.(S) 3. Admin dashboards provide real-time department-level visualization.(M) 4. Dashboards refresh automatically every 5 minutes.(S) 5. Visualizations are responsive and accessible on web browsers."(S) . | S | 2 | Visualization + real-time admin dashboard
|  | Feature 2.5: Export & Sharing Options | 1. As a user, I want to export reports in Excel/PDF formats so that I can share them easily. 2. As a faculty member, I want to schedule automated report generation so that I don’t have to generate them manually every time. 3. As an admin, I want to share reports securely with external stakeholders so that data privacy is maintained. | 1. Reports can be exported in Excel, PDF, and CSV formats.(M) 2. Automated report scheduling (daily/weekly/monthly) is supported.(S) 3. Reports shared externally are encrypted.(M) 4. Users receive confirmation when a report is successfully shared.(S) 5. Exported reports maintain consistent formatting across formats."(S) | S | 2 | Export is easy, encryption adds complexity

## module9
Initiative | Epic | Feature | User Story | Acceptance Criteria | Priority MoSCoW | Estimate | Reasoning
Document Management & File Storage | Epic 2: Document Management & File Storage | Feature 2.1: Secure File Upload | As a user (student/faculty/admin), I want to securely upload project documents and files, so that they are safely stored in the system without risk of unauthorized access. | 1. Files encrypted in storage (M) 2. Unauthorized upload blocked (M) 3. Upload confirmation shown (S) | M | 3 | Core security + encryption setup
|  | Feature 2.2: Version Control | As a student/faculty, I want to upload updated versions of project documents with version history maintained, so that older versions are not lost and changes can be tracked. | 1. System maintains version history (M) 2. User can view/restore old versions (S) 3. No overwriting of files (M) | M | 3 | Needed for project document tracking
|  | Feature 2.3: File Retrieval & Access | As a faculty/admin, I want to easily retrieve submitted project documents from storage, so that I can review and evaluate them without delays. | 1. Search & filter enabled (M) 2. Files open within 3 seconds (S) | M | 2 | Essential for faculty workflows
|  | Feature 2.4: Access Permissions | As an admin, I want to define who can upload, view, and download specific project files, so that confidential documents remain secure and only authorized users can access them. | 1. Role-based permissions enforced (M) 2. Unauthorized access blocked (M) 3. Audit log maintained (S) | M | 3 | Middleware + access control setup
|  | Feature 2.5: Storage Organization | As a user, I want project files to be organized by project, milestone, and team, so that it is easy to navigate and locate required documents. | 1. Folder structure auto-created (M) 2. Sorting & filtering enabled (S) | S | 2 | Improves usability & navigation
|  | Feature 2.6: Large File Support | As a student, I want to upload large project files (presentations, reports, datasets), so that all necessary documents can be submitted without restrictions. | 1. System supports files up to X GB (M) 2. Upload progress bar shown (S) | M | 2 | Handles project datasets & reports
|  | Feature 2.7: Backup & Recovery for Files | As an admin, I want project documents to be regularly backed up and recoverable, so that no critical file is lost during system failures. | 1. Automated daily backup (M) 2. Recovery tested successfully (S) | M | 3 | Prevents data loss
|  | Feature 2.8: Document Preview & Download | As a faculty, I want to preview project documents (PDF, DOCX, PPT) directly in the system before downloading, so that I can quickly review content without downloading every file. | 1. Inline preview supported (M) 2. Supported formats: PDF, DOCX, PPT (M) 3. Quick download enabled (S) | S | 2 | Improves review efficiency
|  | Feature 2.9: Activity Log for File Operations | As an admin, I want every upload, update, and download to be logged with timestamps and user details, so that accountability and transparency are maintained. | 1. Every file event logged (M) 2. Logs visible to admins (M) 3. Export logs supported (S) | M | 2 | Ensures transparency & tracking
|  | Feature 2.10: File Integrity & Security | As a system, I want to scan uploaded files for viruses and ensure encryption in storage, so that data integrity and system security are not compromised. | 1. Virus scan before upload complete (M) 2. Files stored with encryption (M) 3. Alerts triggered for malicious files (S) | M | 3 | Security + compliance